## Sheet1
Tasks | Discipline | Contributors | Due
Design Levels
Level One | Design | Richard Howlett, Paul Hamilton | Week Two
Level Two | Design | Paul Hamilton
Level Three | Design | Richard Howlett
Design Characters
Hitler | Design | Paul Hamilton | Week Two
Stalin | Design | Richard Howlett | Week Two
Fidel Castro | Design | Richard Howlett
Mussolini | Design | Paul Hamilton
Julius Caesar | Design | Richard Howlett
Kim Jong-Il | Design | Paul Hamilton
Robert Mugabe | Design | Richard Howlett
Donald Trump | Design | Paul Hamilton
Design UI
Main Menu | Design | Paul Hamilton, Richard Howlett | Week Two
Character Selection Menu | Design | Richard Howlett
Stage Selection Menu | Design | Richard Howlett
In Game HUD | Design | Richard Howlett
Options Menu | Design | Paul Hamilton
Controls Menu | Design | Paul Hamilton
Match End Menu | Design | Richard Howlett, Paul Hamilton
Design Special Moves
Hitler (close) | Design | Paul Hamilton | Week Two
Hitler (far) | Design | Paul Hamilton | Week Two
Stalin (close) | Design | Richard Howlett | Week Two
Stalin (far) | Design | Richard Howlett | Week Two
Fidel Castro (close) | Design | Richard Howlett
Fidel Castro (far) | Design | Richard Howlett
Mussolini (close) | Design | Paul Hamilton
Mussolini (far) | Design | Paul Hamilton
Julius Caesar (close) | Design | Richard Howlett
Julius Caesar (far) | Design | Richard Howlett
Kim Jong-Il (close) | Design | Paul Hamilton
Kim Jong-Il (far) | Design | Paul Hamilton
Robert Mugabe (close) | Design | Richard Howlett
Robert Mugabe (far) | Design | Richard Howlett
Donald Trump (close) | Design | Paul Hamilton
Donald Trump (far) | Design | Paul Hamilton
Sound
Menus Background Music | Design
Level One Music | Design
Level Two Music | Design
Level Three Music | Design
Sound Effects | Design
Collision Detection
Platforms | Programming | Andrew Peters, Cameron Wallace
Players | Programming | Andrew Peters, Cameron Wallace
Moves | Programming | Andrew Peters, Cameron Wallace
Pickups | Programming | Andrew Peters, Cameron Wallace
Screen Boundaries | Programming | Andrew Peters, Cameron Wallace
Controls
Punch 1 | Programming | Andrew Peters, Cameron Wallace
Punch 2 | Programming | Andrew Peters, Cameron Wallace
Punch 3 | Programming | Andrew Peters, Cameron Wallace
Kick 1 | Programming | Andrew Peters, Cameron Wallace
Kick 2 | Programming | Andrew Peters, Cameron Wallace
Kick 3 | Programming | Andrew Peters, Cameron Wallace
Jump | Programming | Andrew Peters, Cameron Wallace
Throw | Programming | Andrew Peters, Cameron Wallace
Movement (left and right) | Programming | Andrew Peters, Cameron Wallace
Program Special Abilities
Hitler (close) | Programming | Andrew Peters, Cameron Wallace
Hitler (far) | Programming | Andrew Peters, Cameron Wallace
Stalin (close) | Programming | Andrew Peters, Cameron Wallace
Stalin (far) | Programming | Andrew Peters, Cameron Wallace
Fidel Castro (close) | Programming | Andrew Peters, Cameron Wallace
Fidel Castro (far) | Programming | Andrew Peters, Cameron Wallace
Mussolini (close) | Programming | Andrew Peters, Cameron Wallace
Mussolini (far) | Programming | Andrew Peters, Cameron Wallace
Julius Caesar (close) | Programming | Andrew Peters, Cameron Wallace
Julius Caesar (far) | Programming | Andrew Peters, Cameron Wallace
Kim Jong-Il (close) | Programming | Andrew Peters, Cameron Wallace
Kim Jong-Il (far) | Programming | Andrew Peters, Cameron Wallace
Robert Mugabe (close) | Programming | Andrew Peters, Cameron Wallace
Robert Mugabe (far) | Programming | Andrew Peters, Cameron Wallace
Donald Trump (close) | Programming | Andrew Peters, Cameron Wallace
Donald Trump (far) | Programming | Andrew Peters, Cameron Wallace
Pickup Coding
Extra health | Programming | Andrew Peters, Cameron Wallace
Increase Speed | Programming | Andrew Peters, Cameron Wallace
Increase Damage | Programming | Andrew Peters, Cameron Wallace
Increase Defence | Programming | Andrew Peters, Cameron Wallace
Menu Transitions
Play Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace
Controls Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace
Quit Button (Main Menu) | Programming | Andrew Peters, Cameron Wallace
Main Menu Button (every stage) | Programming | Andrew Peters, Cameron Wallace
Character Select Buttons (character select screen) | Programming | Andrew Peters, Cameron Wallace
Rematch Button (End screen) | Programming | Andrew Peters, Cameron Wallace
Quit Button (End Screen) | Programming | Andrew Peters, Cameron Wallace
Back to Character Select Button (End Screen) | Programming | Andrew Peters, Cameron Wallace
General Coding
Health | Programming | Andrew Peters, Cameron Wallace
Damage | Programming | Andrew Peters, Cameron Wallace
Energy to use special moves | Programming | Andrew Peters, Cameron Wallace
Match animations to buttons | Programming | Andrew Peters, Cameron Wallace
Character Modeling
Hitler | Art
Stalin | Art
Fidel Castro | Art
Mussolini | Art
Julius Caesar | Art
Kim Jong-Il | Art
Robert Mugabe | Art
Donald Trump | Art
Level Creation
Level One | Art
Level Two | Art
Level Three | Art
Character Animation
Idle Animation | Art
Punch One | Art
Punch Two | Art
Punch Three | Art
Kick One | Art
Kick Two | Art
Kick Three | Art
Jump | Art
Walk Left | Art
Walk Right | Art
Throw | Art
Being Thrown | Art
Special Ability Animation
Hitler (close) | Art
Hitler (far) | Art
Stalin (close) | Art
Stalin (far) | Art
Fidel Castro (close) | Art
Fidel Castro (far) | Art
Mussolini (close) | Art
Mussolini (far) | Art
Julius Caesar (close) | Art
Julius Caesar (far) | Art
Kim Jong-Il (close) | Art
Kim Jong-Il (far) | Art
Robert Mugabe (close) | Art
Robert Mugabe (far) | Art
Donald Trump (close) | Art
Donald Trump (far) | Art